## Gantt Chart - Meeting Times
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | CNIT 315 Final Project | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Hanna Stolarska, Reed Glenn, Lex Gaylor, Abby Farrell, Quinn Trout | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Project Start: |  | 2023-02-27
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1899-12-31 |  |  | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-02-27 to 2023-05-14
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | MEETING | WHO CAME | PROGRESS | START | END | DAYS | time axis 2023-02-27 to 2023-05-14
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Spring Semester |  | 100% | 2023-02-27 | 2023-05-02 | 65
| Meeting 1 (working on the abstract) | All Members | 100% | 2023-02-27 | 2023-02-27
| Meeting 2 (working on the project description) | All Members | 100% | 2023-03-22 | 2023-03-22
| Meeting 3 (finishing project description and dividing work) | All Members | 100% | 2023-03-29 | 2023-03-29
| Meeting 4 (coding the unit conversion part) | All Members | 100% | 2023-04-05 | 2023-04-05
| Meeting 5 (figuring out the API) | All Members | 100% | 2023-04-12 | 2023-04-12
| Meeting 6 (connecting in the lab) | All Members | 100% | 2023-04-19 | 2023-04-19
| Meeting 7 (working on the GUI, Curl, Presentation) | All Members | 100% | 2023-04-24 | 2023-04-24
| Meeting 8 (working on the presentation and recording it) | All Members | 100% | 2023-04-25 | 2023-04-25
| Meeting 9 (finishing time sheets, working on the functionality of the GUI) | All Members | 100% | 2023-05-01 | 2023-05-01
| Meeting 10 (finishing the project and submitting it) | All Members | 100% | 2023-05-02 | 2023-05-02
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Time Sheet With Explanation
|  | Total Time Spent (Hours) = | 30
| Meeting 1 | Meeting 2 |  | Meeting 3 (Compose Project Description) | Meeting 4 (Coding the Unit Part) | Meeting 5 | Meeting 6 | Meeting 7 | Meeting 8 | Meeting 9 | Meeting 10 | Total Percentage
| 2023-02-27 | 2023-03-22 |  | 2023-03-29 | 2023-04-05 | 2023-04-12 | 2023-04-19 | 2023-04-24 | 2023-04-25 | 2023-05-01 | 2023-05-02
| Hanna | Hanna |  | Hanna | Hanna | Hanna | Hanna | Hanna | Hanna | Hanna | Hanna | Hanna
Task | Compose The Abstract | Discussed Details Concerning Project Description |  | General Overview, Interface | Volume | Did research on the API | Connecting Everything in the Lab | Documenting the meeting / Doing Math For the Tables | Title, Reasoning | Working on the Time Sheets | Working on the Time Sheets Math
Checker | Quinn, Reed, Lex | N/A |  | All Members | Lex, Reed | N/A | N/A | Lex, Reed | All Members | Quinn | Quinn
Total Time Required (Hours ) | 0.5 | N/A |  | 0.5 | 0.5 | N/A | N/A | 0.75 | 0.5 | 1.6 | 1.5 | 19.5%
Time % | 1.667% | 0 |  | 1.667% | 1.667% | 0% | 0% | 2.5% | 1.667% | 5.333% | 5%
Resolution | Accomplished | N/A |  | Accomplished | Accomplished | N/A | N/A | Accomplished | Accomplished | Accomplished | Accomplished
| Reed | Reed |  | Reed | Reed | Reed | Reed | Reed | Reed | Reed | Reed | Reed
Task | Check Abstract | Discussed Details Concerning Project Description |  | Interface, Structures and API | Distance | Did research on the API | Connecting Everything in the Lab | Working on the GUI GTK | UI Implementation, Analysis - Completed Work | GUI Functionality | GUI GTK
Checker | N/A | N/A |  | All Members | Hanna, Lex | N/A | N/A | Abby, Reed | All Members | Lex | Lex
Total Time Required (Hours ) | N/A | N/A |  | 0.5 | 0.5 | N/A | N/A | 1.33 | 0.75 | 1.46 | 1.75 | 20.97%
Time % | 0% | 0% |  | 1.667% | 1.667% | 0% | 0% | 4.433% | 2.5% | 4.867% | 5.833%
Resolution | N/A | N/A |  | Accomplished | Accomplished | N/A | N/A | Accomplished | Accomplished | Accomplished | Accomplished
| Lex | Lex |  | Lex | Lex | Lex | Lex | Lex | Lex | Lex | Lex | Lex
Task | Check Abstract | Discussed Details Concerning Project Description |  | Division of Labor, GUI Implementation-GTK | Speed | Did research on the API | Connecting Everything in the Lab | Working to get the curl running | Interacting With the Program, Technical Components | Research on Implementation of GUI | Working on the Code Menu
Checker | N/A | N/A |  | All Members | Abby, Quinn | N/A | N/A | Hanna, Abby | All Members | Abby | Abby
Total Time Required (Hours ) | N/A | N/A |  | 0.5 | 0.5 | N/A | N/A | 0.9 | 0.75 | 1.6 | 1.5 | 19.17%
Time % | 0% | 0% |  | 1.667% | 1.667% | 0% | 0% | 3% | 2.5% | 5.333% | 5%
Resolution | N/A | N/A |  | Accomplished | Accomplished | N/A | N/A | Accomplished | Accomplished | Accomplished | Accomplished
| Abby | Abby |  | Abby | Abby | Abby | Abby | Abby | Abby | Abby | Abby | Abby
Task | N/A | Discussed Details Concerning Project Description |  | Currency Conversion-API, Unit Conversion-Functions | Weight | Did research on the API | Connecting Everything in the Lab | Working to get the curl running | External API - Exchange Rates, Analysis - Incomplete Work | Parsing Data | Working on / Research Visual Studio
Checker | N/A | N/A |  | All Members | Quinn, Reed | N/A | N/A | Quinn, Lex | All Members | Reed | Hanna
Total Time Required (Hours ) | N/A | N/A |  | 0.5 | 0.5 | N/A | N/A | 0.75 | 0.5 | 1.5 | 2.5 | 20.83%
Time % | 0% | 0% |  | 1.667% | 1.667% | 0% | 0% | 2.5% | 1.667% | 5% | 8.333%
Resolution | N/A | N/A |  | Accomplished | Accomplished | N/A | N/A | Accomplished | Accomplished | Accomplished | Accomplished
| Quinn | Quinn |  | Quinn | Quinn | Quinn | Quinn | Quinn | Quinn | Quinn | Quinn | Quinn
Task | Check Abstract | Discussed Details Concerning Project Description |  | Unit Conversion, Structures and API | Temperature | Did research on the API | Connecting Everything in the Lab | Working on the GUI GTK | Functionality, Examples of the Code | Working on the Time Sheets | Research Visual Studio / Working on the Code Menu
Checker | N/A | N/A |  | All Members | Hanna, Abby | N/A | N/A | Hanna, Lex | All Members | Hanna | Reed
Total Time Required (Hours ) | N/A | N/A |  | 0.75 | 0.75 | N/A | N/A | 0.53 | 0.6 | 1.33 | 1.9 | 19.53%
Time % | 0% | 0% |  | 2.5% | 2.5% | 0% | 0% | 1.767% | 2% | 4.433% | 6.333%
Resolution | N/A | N/A |  | Accomplished | Accomplished | N/A | N/A | Accomplished | Accomplished | Accomplished | Accomplished
Total Meeting Time (Hours) | 0.5 | 3 |  | 2.5 | 2.5 | 2.5 | 2 | 3.5 | 3.5 | 5 | 5 | Together
100%
Note:
The Total Time Required equals the time that each person spent on their task. Members took on specfific tasks at every meeting. Although the time spent on one's task may be only half an hour, each member stayed the full time at each meeting and helped out other team members with tasks or discussed the next steps. The total time required represents how much time each team member spent on their respective tasks at each meeting. On the days when all members worked on the same task, I decided not to record individual times spent.